MINUTES

WEDNESDAY, DECEMBER 19, 2018

MONTGOMERY COUNTY REGIONAL SEWER DISTRICT

South Boulevard County Building

110 W South Boulevard

Crawfordsville, IN  47933

The Montgomery County Regional Sewer District met in regular session on Wednesday, December 19, 2018 at 8:30 a.m. at the South Boulevard County Building, 110 W South Boulevard, Crawfordsville, Indiana.  Present were Board members: Chairman Phillip Bane, Vice Chairman Terry Hockersmith, Brad Monts, Secretary/Co-Treasurer, and Joe McCutcheon, Member.

Also present Sam Webber & Stan Hamilton, VS Engineering; Montgomery County Building Administrator Marc Bonwell; Montgomery County Engineer Jim Peck; Tom Astbury, Astbury Water Technologies; Don Orr – Health Department, Mike Keeven & Julie Petrie-DLZ Representative; Scott Siple-Nucor Engineer; District Attorney Stu Weliever - Weliever, Henthorn, Harris, Weliever & Petrie, LLC; County Commissioner John Frey; and RDC Attorney Dan Taylor.

I.      Call to Order - Chairman Phil Bane called the meeting to order at 8:30 am.

II.    Minutes

The minutes of the November 21, 2018 regular meeting. Brad Monts moved to approve.  Terry Hockersmith seconded.  Motion passed 4-0.

III.   Astbury Monitoring Report

Tom Astbury advised that the WWTP has maintained at 53% capacity with a reading as 	high as 83,000 to the lowest as 38,000.

IV.   VS Engineering Report

Sam Webber, P.E. reviewed with the board the November, 2018 Monthly Report.  		{See Attached}. Mr. Webber stated that they are continuing to work with a conflict with 	the utility coordination with AT&T to resolve a conflict in front of Pilot on SR32.  Two 	options:

1)  Extend the jack and bore operation another 100’.  This will avoid the conflict 	but 	cost an additional cost of $70,000 aka 700’.  No easements will be necessary; or

2)  Obtain easements from Sixberry Services and Pilot.  Shift alignment outside the 	ROW.  Additional costs for easements estimated around $20,000.

V.    SR32/CR400E Sewer Expansion Construction Project Report

DLZ Construction Inspector Julie Petree advised one crew is starting to clear trees for 	the lift 	station area to accommodate the 12” sewer main.  The pipes have been laid up to 	CR400 	and Nucor Road.  Miller Pipeline will finish out this week if the weather 	cooperates and will not be back to complete the project until after the 1st of the year.  	Testing of the low pressure system on SR32 will be the next step.

VI.   Nucor Road WWTP Capacity Analysis Update – Shannon Killion - GAI

Shannon Killion advised that they have been reviewing various MRO data and have

noticed mass loading with “lots” of variation.  There is a high concentration of ammonia 	at times and those spikes cannot be ignored going forward.  Tom Astbury added that 	they would recommend a semiannual pre-treat spot check.  Killion continued that 	Chigger Hollow Subdivision only accounts for 6% of the load.  Asbury stated that they 	have concentration readings for Pilot and BANJO.

VII.    Request for Clarification re: B&B Sewage User Rate – 2710 E State Road 32 - Owner 	Isaac Hook

Mr. Hook expressed concern and questions regarding the STEP Agreement for the Early 	Bird sign up.  He has a water meter and based on his water consumption, he would not 		exceed the EDU under the current ordinance.  He stated the STEP Agreement states a 	200’ lateral is included and anything beyond 200’ is the responsibility of the landowner.

He is not getting the same answers to his questions and asked for clarification from the 	Board.  Attorney Weliever will work on a proposed revised STEP Agreement taking into 	account that Mr. Hook’s Bed & Breakfast does not fall under the Hotel estimated EDU’s 	as stated in the ordinance.

VIII.	Resolution 2018-5 – A Resolution Consenting to Provision of Water Service by 	Indiana American Water in Infrastructure Development Zone 1

Redevelopment Commission Attorney Dan Taylor explained the purpose of Resolution 	2018-5 is to have the consent of the Regional Sewer District to request the County 	Commissioners consent to Indiana American Water Company, Inc. providing water 	infrastructure and facilities in the limited area to be designated Infrastructure 	Development Zone.

Brad Monts moved to approve Resolution 2018-5 as presented.  Joe McCutcheon seconded.  	Motion passed 4-0.  {Resolution 2018-5}

IX.   Treasurers Report

A.  SR32/Nucor Road Sewer Expansion Collection System Construction Claims

Payee			Invoice #	 Amount 	Date

DLZ			823997	 	$18,187.19 	11/30/2018

Eagle Valley, Inc.	1830-2	 	$161,660.84 	12/12/2018

TOTAL	 $179,848.03

Terry Hockersmith moved to recommend approval of the DLZ & Eagle Valley, Inc. claims in the 	amount of $179,848.03 to the Redevelopment Authority for payment.  Brad Monts seconded.  	Motion 	passed 4-0.

B.  Approve Accounts Payable Claims - $41,008.43

Brad Monts moved to approve claims as presented in the amount of $41,008.43.  Terry 	Hockersmith seconded.  Motion passed 4-0.  {See Attached}

Current Bank Balance: $280,038.11.

X.     Other Business

Building Administrator Marc Bonwell advised his office has been contacted by a prospective buyer of property on CR350S with questions about the availability of sewer and what the connection fee would be.  After discussion with the Board, they advised that they will have to look into the engineering options.

XI.    Adjourn

Having no other business to come before the Board, Joe McCutcheon moved to adjourn the meeting.  Terry Hockersmith seconded. The motion passed 3-0.

The meeting adjourned @ 9:25 a.m.

Next regular meeting to be held on Wednesday, December 19, 2018 @ 8:30 am

Respectfully Submitted by Recording Secretary

Laura Dossett

Co-Treasurer - MCRSD

Approved this 19th day of December, 2018

______________________________________

Phillip Bane Chairman